## Sheet1
Task | Start Date | Days to Complete
Integrate old Lab Work (GJ) | 2018-11-06 | 2
Client GUI | 2018-11-08 | 2
Server GUI | 2018-11-08 | 2
Start Game GUI and functionality (AJ) | 2018-11-08 | 2
Gameplay GUI | 2018-11-08 | 4
Bet GUI | 2018-11-08 | 4
Database Creation | 2018-11-08 | 2
Database Communication | 2018-11-10 | 4
Gameplay Functionality | 2018-11-12 | 9
Bet Functionality | 2018-11-12 | 8
Unit Testing (all) | 2018-11-21 | 3
Integration Testing (all) | 2018-11-24 | 5
Final Testing (all) | 2018-11-29 | 4